## Slide 1: Innovation #665 Hazardous Pharmaceuticals Project Kickoff Meeting
February 19, 2013
Notes: Presented by:
Don Michalak, PMP, CSM
New Models of Health Care, OED
Albany, OIFO
518-449-0242 (office)
Feel free to use all or some of this presentation but give credit to the appropriate source and authors to avoid any copyright issues.

## Slide 2: Agenda
VA Introductions & Opening Remarks (Kristopher Teague)
HPES Introductions & Opening Remarks (John Walsh)
Overview of Project (Margaret Raisch)
Overview of Contract (Niha Goyal)
Project Management Plan (Niha Goyal)
On-boarding status (Niha Goyal)
COR Items (Kristopher Teague)
Reporting & Reviews (John Walsh)
Other Project Topics (Niha Goyal)
Questions
Wrap –Up & Action items

## Slide 3: Introductions & Opening Remarks
Department of Veterans Affairs (VA)
Technology Acquisition Center (TAC)
Matthew Ginty (HPES Contract Officer) - Matthew.Ginty@va.gov
Meghan McCloskey (HPES Contract Specialist) - Meghan.Mccloskey@va.gov
Kendra Archbald (Project Contract Officer) - Kendra.Archbald@va.gov
Matthew Newell (Project Contract Specialist) - Matthew.Newell@va.gov
Janet Colyard (Procurement Coordinator) - Janet.Colyard@va.gov
Innovation #665 Hazardous Pharmaceuticals Team
Kristopher "Kit" Teague (PM and COR) – Kristopher.Teague@va.gov
Craig Davis (Innovation) - craig.davis3@va.gov
Michael Cortright (Innovation) - michael.cortright@va.gov
Margaret Raisch (Project Lead) - margaret.raisch@va.gov
George Knight (SME) - george.knight@va.gov

## Slide 4: Introductions & Opening Remarks
Innovation #665 Hazardous Pharmaceuticals SME Team
Name Area Representing E-Mail____________________________________
Carolyn Gutowski Industrial Hygiene Carolyn.Gutowski@va.gov
Jack Staudt Environmental Jack.Staudt@va.gov
Bill Kulas Environmental William.Kulas@va.gov
Vaiyapuri Subramaniam Pharmacy Vaiyapuri.Subramaniam@va.gov
George Knight Pharmacy George.Knight@va.gov
Bob Van Arsdale Pharmacy Robert.Vanarsdale@va.gov
John Lechman Health & Safety CMOP John.Lechman@va.gov
Dick Hoffman Industrial Hygiene
Dan Erwin Industrial Hygiene Daniel.Erwin@va.gov
Clarice Grens Nursing Clarice.Grens@va.gov
Ruth Gholz Nursing Ruth.Gholz@va.gov
Rob Silverman Pharmacy Informatics, PBM Robert.Silverman@va.gov
Don Lees Pharmacy Informatics, PBM Don.Lees@va.gov

## Slide 5: Introductions & Opening Remarks
HP Enterprise Services, LLC
Barry Keiser (Account Executive) – barry.keiser@hp.com
Carol Greening (Account Manager) – carol.greening@hp.com
Jay Heroux(Client Sales Executive) – jay.heroux@hp.com
Maria Meleca (MHVA ePMO Leader) – maria.kirk@hp.com
Nicole Watt (MHVA ePMO Delivery Assurance Manager) – nicole.watt@hp.com
Terrie Hohimer (ePMO Security Clearance Lead) - terrie.hohimer@hp.com
Brittany Jackson (ePMO Project Lead) - brittany.jackson@hp.com
Geff Garnhart (T4 Project Director) – geff.garnhart@hp.com
Katie Bowen (T4 Deputy Project Director) – katie.bowen@hp.com
John Walsh (T4 PMO) – john.walsh3@hp.com
Nana Frimpong (Contracts Manager) – nana.frimpong@hp.com
Niha Goyal (Program Manager) - niharika.goyal@hp.com
Yuki Olinger (Project Manager) – yuki.olinger@hp.com

## Slide 6: Project Team
Key Personnel:
  Program Manager – Niha Goyal
  Project Manager – Yuki Olinger
  Business Analyst – Marla Newman
  Delphi Developer – Bob Kaiser
  Mumps Developer – John Castle
  Java Developer – Anand Narayanaswamy
  System Administrator – Bob Steidl
  DBA – Alicia Ray
  SQA – Zafar Kazi
  Technical Writer – Kiley Kapple

## Slide 7: Overview of Project
Development of a prototype
All work is accomplished in VA’s Innovation Sandbox
Following applications to be enhanced:
  Pharmacy Product System – National (PPS-N)
  National Drug File
  BCMA
Identify and create alerts for drugs and supplies:
  Hazardous to handle
  Hazardous to dispose
Business Value: Prevent hazards for human exposure and environmental hazards upon disposal

## Slide 8: Overview of Contract
Task Order 0114: titled, “Innovation #665 Hazardous Pharmaceuticals”
  This performance-based Task Order 0008 titled, “Innovation #665 Hazardous Pharmaceuticals” is issued on a Firm-Fixed-Price (FFP) basis, in accordance with the terms and conditions of Contract VA118-11-D-1014 and modifications thereto. The TAC Number associated with this task is TAC-13-05296.
The Task Order period of performance is:
  Base Period: February 7, 2013-October 6, 2013
  Option Period: None
Prime Contractor is HPES
  Sub-contractor: Flexion Inc.
HPES will provide:
  Program management, Systems/Software Engineering, Software Technology Demonstration and Transition, Test and Evaluation

## Slide 9: Project Management
Major Deliverables:
  Roster (02/08/2013)
  Technical Kick off Agenda 2/14/13
  Technical Kick off Meeting Minutes 2/22/13
  Project Management Plan 3/7/13
  Monthly reports starting 3/15/13
  GFE Report due every 15th of the month
  Small Business Report (Quarterly)
  Requirements Document 5/8/13
  Design Document 5/8/13
  PPS-N Installation
  Milestone Reviews
  Prototype Demo

## Slide 10: On-boarding Status
10 Resources for the Project
  9 from HPES
  1 Tech writer resource from Flexion
Government Furnished Equipment (GFE)
  Not Applicable, folks will be accessing the VA Sandbox – outside of VA firewall
Non-Disclosure Agreement (NDA)/PIV/Security
  The identified resources are already onboard and have clearance
  Reciprocity packets sent to COR

## Slide 11: COR Items
COR Role in this Project
  COR is Eyes and Ears of the CO
  Receive and Evaluate Deliverables (as part of SME Team)
  Certify Invoices
  Help Resolve Problems, Issues, or Delays
  Maintain Scope of Work
  Consult with CO when Contractual Issues Arise (Scope Issues, Modifications, etc.)
On-Boarding Requirements
  Status of On-Boarding Package Reviews
  Annual Mandatory Training Updates
  Reciprocation Request with VA SIC
Sandbox Access and Setup
  Web Help Desk Accounts and Sandbox Accounts (Wikis and Persistent Virtual Environment)
  Technical Sandbox Call with Craig Davis
  Working on Getting Information on NDF/PPS-N Install

## Slide 12: COR Items (cont.)
Deliverable and Invoice Submissions
  All Deliverables should be Sent to Innovator, COR, and SME Team (CO is Optional Unless They Deem Necessary).
  The COR should be Given a “Heads-Up” before an Invoice is Submitted. This will Ensure Timely Certification and Payment.
Important Contract Clauses
  6.2 Communications/Public Affairs (Page 29 of Task Order)
Lines of Communication
  Clear Lines of Communication are Necessary to Stay Ahead of Problem
  As COR and VA PM, my Preferred Line of Communication is with the HP PM Only. This Way Both PMs (VA and HP) are Aware of All Issues at All Times.
  Issues should be Documented in Issue Log and Discuss as an Action Item at Bi-Weekly Meeting until a Resolution is Reached.

## Slide 13: Reporting & Reviews
Quarterly Prime Reviews
  Provide overall programmatic status and updates
  Ensure consistency across all Primes
  Discuss and resolve issues effecting all Primes
Program Monthly Reviews
  Monthly Meetings with individual Primes
  Review of Each Task Order
  Discussions/Review of issues unique to the Contractor
BI-WEEKLY MEETINGS
  Bi-weekly meetings and minutes (will be held on Thursdays via Live Meeting; Time TBD)
Reports
  Small Business Participation Report due quarterly on the 15th
  Monthly Progress, Status and Management Report due on the 15th
  Manpower Report due every month on the 15th
  GFE due every month on the 15th

## Slide 14: Other Project Topics
Software for PPS-N installation in Sandbox
  We listed the software we need to do the PPS-N installation in the Sandbox in the ODC section of our pricing proposal
  If some or all of that software is already in the Sandbox, a contract modification will be necessary to decrease the amount of software that is needed to be purchased

## Slide 15
Questions?

## Slide 16
Wrap up and Action Items